## Test Scenario
Project Name | Pickaboo.com
Reference Document | FRS
Created By | Suvojit Das
Creation Date | 2024-05-04
Approval Date | 20/04/2024
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test cases
TS_001 |  | Validate the URL and features in differnet browsers and OS | PO | 1
TS_002 |  | Validate the "Register" functionality | PO | 58
TS_003 |  | Validate the working of "Sign in" functionality | PO | 40
TS_004 |  | Validate the features in default characteristics | PO | 4

## TestCase
Product Name |  | Pickaboo | TC Start Date | 2024-05-04 | TC Execution Start Date | 2024-07-05 |  |  |  | TEST CASE
Module Name |  | Sign Up and Sign In | TC End Date | 20/04/2024 | TC Execution End Date | 2024-11-06 |  |  |  | Pass | 83
Epic |  |  | Test Case Developed By | Suvojit Das | Browser (tested) | Yes |  |  |  | Fail | 19
Developer Name (TL) |  |  | Test Case Reviewed By | Ehsanul Alam Sabbir | Performance (tested) | No |  |  |  | Not Executed | 1
Test Executed by |  | Suvojit Das | [7 empty] | Out of Scope | 0
[10 empty] | TOTAL | 103
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Final Status
1 | User Management | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Internet Explorer Mozilla Firefox Microsoft Edge Brave |  |  | Passed
2 |  | UI Testing | Register | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A |  |  | Passed
3 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A |  |  | Passed
4 |  |  |  | Checking if all necessary elements are visible on the Register page | All the elements should be visible | Found as per expectation | N/A |  |  | Passed
5 |  |  |  | Veryfing that input fields are accepting the correct type of data | Should be as per the requirement | Found as per expectation | N/A |  |  | Passed
6 |  |  |  | Checking that appropriate error messages are displayed when invalid data is entered into the fields. | Sould be displayed error message on the page | Found as per expectation | N/A |  |  | Passed
7 |  |  |  | Checking that the username and password fields are visible and editable. | Should be as per the requirement | Found as per expectation | N/A |  |  | Passed
8 |  |  |  | Checking Alignment of the Fields | Proper alignment of the fields should be present | Found as per expectation | N/A |  |  | Passed
9 |  |  |  | Checking proper instruction for inavild or blank phone number in alert message. | Should be show proper instructions | Not found as per expectation | N/A | 1. Goto the URL https://www.pickaboo.com/register/ 2. Click on Login button at the right corner then goto register/ 3. Inputting firstname and lastname with numbers 4. Click Contniue button without input any number | https://www.loom.com/share/79f2bc79a3674d789b4feb868687aede?sid=0d336079-e395-4f61-9f0b-ae10cb052eb4 | Failed
10 |  |  |  | Checking that the "Register Continue" button is disabled until all mandatory fields are filled correctly | Should be disabled | Not found as per expectation |  | 1. Goto the URL https://www.pickaboo.com/register/ 2. Click on Login button at the right corner then goto register/ 3. Inputting firstname and lastname and blank mobile number field 4. see contiue button | https://drive.google.com/file/d/1zmRppI1N-N1Nx4tcXHPwqthlnDJ7rFJg/view?usp=drive_link | Failed
11 |  |  |  | Checking 'send' button is enabled by default | Should be enabled by default | Found as per expectation | N/A |  |  | Passed
12 |  | Functionality Testing |  | Checking with creating Blank Space in First Name and Last Name Fields | Should not accept blank | Not found as per expectation |  | 1. Goto the URL https://www.pickaboo.com/register/ 2. Click on Register button at the right Login corner 3. Blank first name and last name box. 4. Then input Valid phone number and send | https://drive.google.com/file/d/18kwGYX-wlT3DYoKYP2T5acHKQoLVTTr6/view?usp=sharing | Failed
13 |  |  |  | Checking duplicate value both first name and last name | Should not accept the provided input | Not found as per expectation | Stephen Stephen | 1. Goto the URL https://www.pickaboo.com/register/ 2. Click on Register button at the right Login corner 3. Blank first name and last name with same input name 4. Input phone number 5. Click Contniue | https://drive.google.com/file/d/1Vl_Jm19uORgv0gXMgcpbvkgLj73xxi-y/view?usp=drive_link | Failed
14 |  |  |  | Checking with creating Blank Space at First Position Before First Name and Last Name | Should not accept the provided input | Not found as per expectation | Stephen Martinez | 1. Goto the URL https://www.pickaboo.com/register/ 2. Click on Register button at the right Login corner 3. Blank first postion in firstname and lastnamefield. 4. input "space" Stephen and "Space" Martinez 5. Then input valid phone number and contiue | https://www.loom.com/share/e4956e9fd5b2464b82bfbc3d58902d04?sid=3a3f3d10-5f84-4ea2-bd61-06923ee19dd6 | Failed
15 |  |  |  | Checking with creating Blank Space at Last Position after First Name and Last Name | Should not accept the provided input | Not found as per expectation | Stephen Martinez | 1. Goto the URL https://www.pickaboo.com/register/ 2. Click on Register button at the right Login corner 3. Blank last postion in firstname and lastnamefield. 4. input Stephen "space" and Martinez "Space" 5. Then input valid phone number and contiue | https://drive.google.com/file/d/1wlsVUYLn5oJ-DCvv-PS7GCqUjtHb4IX8/view?usp=drive_link | Failed
16 |  |  |  | Checking confirmation OTP sent to the Valid mobile number | Sent successfully | Found as per expectation | N/A |  |  | Passed
17 |  |  |  | Checking entering invalid mobile number | Should not accepted | Found as per expectation | 1028589508 |  |  | Passed
18 |  |  |  | Checking that the field accepts a valid 11-digit mobile number | Should be accept | Found as per expectation | 1728589508 |  |  | Passed
19 |  |  |  | Checking the field rejects entries with letters or special characters | Should not accepted | Found as per expectation | 01728@95088 |  |  | Passed
20 |  |  |  | Checking that the field does not accept numbers with Except BD country codes | Should not accepted | Found as per expectation | 918617219818 |  |  | Passed
21 |  |  |  | Inputting firstname and lastname with special characters | Should not accepted | Not found as per expectation | St@ephen Mar@tinez | 1. Goto the URL https://www.pickaboo.com/register/ 2. Click on Login button at the right corner then goto register/ 3. Inputing firstname and lastname with special characters | https://drive.google.com/file/d/1PQMj1W9v5MkVbziAXHitQY8_FwPCFj__/view?usp=sharing | Failed
22 |  |  |  | Inputting numbers in firstname and lastname. | Should not accept the provided input | Not found as per expectation | 8888888 89999 | 1. Goto the URL https://www.pickaboo.com/register/ 2. Click on Login button at the right corner then goto register/ 3. Inputting firstname and lastname with numbers | https://drive.google.com/file/d/1-UA7h7K45tCO0ZN3bDC58XL-8ynPStWK/view?usp=sharing | Failed
23 |  |  |  | Inputing decimal numbers in firstname and lastname | Should not accept the provided input | Not found as per expectation | 74.78 56.43 | 1. Goto the URL https://www.pickaboo.com/register/ 2. Click on Login button at the right corner then goto register/ 3. Enter decimal number in firstname and lastname field | https://drive.google.com/file/d/1Rf8qKIOvhjINHdrbA4mUdsq0wjLoAyXZ/view?usp=sharing | Failed
24 |  |  |  | Inputting firstname and lastname with alphanumeric characters | Should not accept the provided input | Found as per expectation | Stephen88 Martinez44 | 1. Goto the URL https://www.pickaboo.com/register/ 2. Click on Login button at the right corner then goto register/ 3. Enter alphanumeric characters in firstname and lastname field | https://drive.google.com/file/d/1FPxx7Un0glx9EaFBR0x3qcZddUDSiQ8b/view?usp=sharing | Failed
25 |  |  |  | Inputting firstname and lastname with alphabets | Should accept the provided input | Found as per expectation | Stephen Martinez |  |  | Passed
26 |  |  |  | Entering comma between alphabets for firstname and lastname | Should not accept the provided input | Not found as per expectation | Stephen,sss Martinez,mm | 1. Goto the URL https://www.pickaboo.com/register/ 2. Click on Login button at the right corner then goto register/ 3. Entering comma between alphabets for firstname and lastname | https://drive.google.com/file/d/1jQFhRzVgNSOE3Oi62bEPnPTJvxQQgtKa/view?usp=sharing | Failed
27 |  |  |  | Entering space between alphabets for firstname and lastname | Should accept the provided input | Found as per expectation | Stephen Davis Martinez |  |  | Passed
28 |  |  |  | Entering space between alphabets for firstname and lastname | Should not allow user to register next time | Found as per expectation | Stephen Martinez 01728589508 |  |  | Passed
29 |  |  |  | Checking password with valid password format | Should accept the provided input | Found as per expectation | SM1234 |  |  | Passed
30 |  |  |  | Checking password with entering letter | Should not accept the provided input | Not found as per expectation | abcdef | 1. Goto the URL https://www.pickaboo.com/register/ 2. Click on Login button at the right corner then goto register/ 3. Inputting password with letter on password fild of register page 4. Click Contniue | https://drive.google.com/file/d/19a5I2QH5y6j4JLVFTso3nblY4cg3iD95/view?usp=sharing | Failed
31 |  |  |  | Checking password with entering number | Should not accept the provided input | Not found as per expectation | 123456 | 1. Goto the URL https://www.pickaboo.com/register/ 2. Click on Register button at the right Login corner 3. Inputting number on password field "123456" 4. Click Contniue | https://drive.google.com/file/d/1V6-KYT8i7bIrlAETPiPXX-bugENAUAzA/view?usp=sharing | Failed
32 |  |  |  | Checking password with entering special character | Should not accept the provided input | Not found as per expectation | SM@123 | 1. Goto the URL https://www.pickaboo.com/register/ 2. Click on Register button at the right Login corner 3. Inputting number on password field ,password is"SM@123" 4. Click Contniue | https://drive.google.com/file/d/1A7-CP1QEBTt-HbAhDsdZbpL7pBtrHEPn/view?usp=sharing | Failed
33 |  |  |  | Checking password with entering blank space between character and letter | Should not accept the provided input | Not found as per expectation | SM 123 | 1. Goto the URL https://www.pickaboo.com/register/ 2. Click on Register button at the right Login corner 3. Inputting number on password field ,password is"SM 123" 4. Click Contniue | https://drive.google.com/file/d/1bx-FvT1-OJYkc0r3XsKikd9fXHisFRpl/view?usp=sharing | Failed
34 |  |  |  | Checking password with decimal number | Should not accept the provided input | Not found as per expectation | 78.9 | 1. Goto the URL https://www.pickaboo.com/register/ 2. Click on Register button at the right Login corner 3. Inputting 78.9 on password field 4. Click Contniue | https://drive.google.com/file/d/11mbYLws59fsRmmKrslKRDFBYdXpjW2na/view?usp=sharing | Failed
35 |  |  |  | Checking password entering 5 character | Should not accept the provided input | Not found as per expectation | EQ231 | 1. Goto the URL https://www.pickaboo.com/register/ 2. Click on Register button at the right Login corner 3. Inputting EQ231 on password field 4. Click Contniue | https://drive.google.com/file/d/1qTv5VtW6WJWSigY2k9rs_bpQnn2Mo91F/view?usp=sharing | Failed
36 |  |  |  | Checking password entering 7 character | Should accept the provided input | Found as per expectation | EQ2318Y |  |  | Passed
37 |  |  |  | Inputing different data for password and confirm password | Should not allow user to register and display a pop message | Found as per expectation | 01728589508 666666666 |  |  | Passed
38 |  |  |  | Inputing valid data for password and confirm password | Should allow user to register | Found as per expectation |  |  |  | Passed
39 |  |  |  | Verifying with valid email address | Should accept the provided input | Found as per expectation |  |  |  | Passed
40 |  |  |  | Verifying with invalid email address | Should not accept the provided input | Not found as per expectation | thtzdxgrgxcxd | 1. Goto the URL https://www.pickaboo.com/register/ 2. Click on Register button at the right Login corner 3. Inputting thtzdxgrgxcxd on password field 4. Click Contniue | https://drive.google.com/file/d/1s_6CFD5MPbeNa_cjBsZN6svsKN7OmbGz/view?usp=drive_link | Failed
41 |  |  |  | Verifying email field with valid domain | Should accept the provided input | Found as per expectation | firstname.lastname@company.org |  |  | Passed
42 |  |  |  | Verifying email with valid subdomain | Should accept the provided input | Found as per expectation | contact@subdomain.website.net |  |  | Passed
43 |  |  |  | Checking the field accepts emails with a plus sign | Should accept the provided input | Found as per expectation | user+tag@example.com |  |  | Passed
44 |  |  |  | Checking the field rejects emails without a TLD | Should not accept the provided input | Found as per expectation | user@example |  |  | Passed
45 |  |  |  | Verifying that the field rejects emails with consecutive dots | Should not accept the provided input | Found as per expectation | user..name@example.com |  |  | Passed
46 |  |  |  | Checking that the field accepts emails with numeric TLDs | Should accept the provided input | Found as per expectation | user@example.123 |  |  | Passed
47 |  |  |  | Checking that the field accepts emails with different top-level domains | Should accept the provided input | Found as per expectation | 2271553@stud.kuet.ac.bd |  |  | Passed
48 |  |  |  | Checking 'Terms and condition' is working | Should be showing terms and conditions | Found as per expectation |  |  |  | Passed
49 |  |  |  | Checking 'privacy policy' is working | Should be showing privacy policy | Found as per expectation |  |  |  | Passed
50 |  |  |  | Checking 'privacy policy' is working | Should be showing privacy policy | Found as per expectation |  |  |  | Passed
51 |  |  |  | Verifying that clicking the ‘Sign in with Facebook’ button redirects to the Facebook login page | Should allow user to register | Found as per expectation | Click on 'Facebook' button |  |  | Passed
52 |  |  |  | Verifying that clicking the ‘Sign in with Google’ button redirects to the Google authentication page | Should allow user to register | Found as per expectation | Click on 'Google' button |  |  | Passed
53 |  |  |  | Checking that users can sign in successfully using their Google account credentials | Should allow user to register | Found as per expectation | N/A |  |  | Passed
54 |  |  |  | Checking that users can sign in successfully using their Facebook account credentials. | Should allow user to register | Found as per expectation |  |  |  | Passed
55 |  |  |  | Checking 'privacy policy' is working | Should be showing privacy policy | Found as per expectation |  |  |  | Passed
56 |  | Usability Testing |  | Checking copy paste functionality in every field | Should copy and paste | Functioning successfully |  |  |  | Passed
57 |  |  |  | Checking that upon successful registration, the user receives a clear confirmation mail or text | Should sent confirmation mail or text | Found as per expectation |  |  |  | Passed
58 |  |  |  | Checking that all elements of the registration page are accessible to users | Should be accessible | Found as per expectation |  |  |  | Passed
59 |  |  |  | Checking Autofill option | User should be filled input field using Autofill option | Found as per expectation |  |  |  | Passed
60 |  | UI Testing | Sign In | Checking that the mobile number box is visible on the login page | Should be visiable | Found as per expectation |  |  |  | Passed
61 |  |  |  | Checking that the password box is visible on the login page | Should be visiable | Found as per expectation |  |  |  | Passed
62 |  |  |  | Checking that the Login button is clearly visible on the login page | Should be visiable | Found as per expectation |  |  |  | Passed
63 |  |  |  | Checking the alignment every boxes. | Should be aligned | Found as per expectation |  |  |  | Passed
64 |  |  |  | Checking that the text color and background color of the every input box have sufficient contrast for easy readability | Should be readable | Found as per expectation |  |  |  | Passed
65 |  |  |  | Checking spelling or grammatical mistakes | Should be no spelling or grammatical mistake | Found as per expectation |  |  |  | Passed
66 |  |  |  | Checking that appropriate error messages are displayed when invalid data is entered into the fields. | Sould be displayed error message on the page | Found as per expectation |  |  |  | Passed
67 |  | Functionality Testing |  | Checking with keeping email and password field blank | Should not allow user to login | Found as per expectation | N/A |  |  | Passed
68 |  |  |  | Checking login valid credentials in email and password field | Should allow user to login | Found as per expectation | 01728589508 Pass |  |  | Passed
69 |  |  |  | Checking login wrong credentials in password field | Should not allow user to login and display an error messeage | Found as per expectation | 01728589508 Wrong pass |  |  | Passed
70 |  |  |  | Checking the user receives a password reset email or SMS with a reset link or code | Should received email or OTP | Found as per expectation |  |  |  | Passed
71 |  |  |  | Checking that the user can successfully set a new password and subsequently log in with it | Should successfully set new password | Found as per expectation |  |  |  | Passed
72 |  |  |  | Verifying change the password link is sent to valid registered mobile number | Should be sent to valid registered mobile number | Found as per expectation |  |  |  | Passed
73 |  |  |  | Veryfing that when a non-registered mobile number is entered for password reset | Should not allow for non registered number | Found as per expectation |  |  |  | Passed
74 |  |  |  | Verifying that an appropriate error message is displayed when an invalid mobile number format is submitted. | Should be dispayed error message | Found as per expectation | N/A |  |  | Passed
75 |  |  |  | Veryfing that the password reset OTP expires after a certain period or after use | Should not allow to use again | Found as per expectation | N/A |  |  | Passed
76 |  |  |  | Checking that the password reset process is terminated if the user navigates away from the page before completion. | Should be terminated | Found as per expectation |  |  |  | Passed
77 |  |  |  | Verifying that the user cannot reuse an old password | Should not allow to use again | Found as per expectation |  |  |  | Passed
78 |  |  |  | Verifying the functionality of 'Set a New Password' | Should provide a new input for setting new password | Found as per expectation | N/A |  |  | Passed
79 |  |  |  | Checking by selecting ‘Forgot Password’ multiple times | Account should be temporarily restricted and a message should be displayed | Found as per expectation with a message | N/A |  |  | Passed
80 |  |  |  | Verifying login with the newly changed password | Should allow user to login | Found as per expectation |  |  |  | Passed
81 |  |  |  | Chceking that clicking the “Register Here” button redirects the user to the registration page | Should be redirect | Found as per expectation |  |  |  | Passed
82 |  |  |  | Chceking that registration page has all the necessary fields for a new user to create an account. | Should be have necessary field | Found as per expectation |  |  |  | Passed
83 |  |  |  | Checking that the system identifies and prevents the creation of duplicate accounts using the same mobile number. | Should not allow to use again | Found as per expectation |  |  |  | Passed
84 |  |  |  | Verifying that the Login Button is enabled when both the mobile number and password fields are filled out with valid data. | Should be enabled | Found as per expectation | 01728589508 Valid Pass |  |  | Passed
85 |  |  |  | Checking that if clicking the Login Button successfully logs in the user when valid credentials are provided. | Should be login | Found as per expectation |  |  |  | Passed
86 |  |  |  | Verifying that the Login Button is disabled when either the mobile number or password field is left empty. | Should be disabled login button | Not Found as per expectation |  | 1. Goto the URL https://www.pickaboo.com/register/ 2. Click on Register button at the right Login corner 3. Empty password or mobile number field 4. see contiue button still visible | https://drive.google.com/file/d/1UkqbAtkjnOhVRNyCbwPmKGCFpZKLKVUl/view?usp=drive_link | Failed
87 |  |  |  | Verifying that the login is unsuccessful when either the mobile number or password field is left empty. | Should be shown error message | Found as per expectation |  |  |  | Passed
88 |  |  |  | Checking if the user is presented with the Google authentication page. | Should be displayed | Found as per expectation |  |  |  | Passed
89 |  |  |  | Checking that that user is automatically logged out after the session expires. | Should be expires | Found as per expectation |  |  |  | Passed
90 |  | Usability Testing |  | Verifying that any instructions on the login page are clear and easy to understand. | Should be understandable | Found as per expectation |  |  |  | Passed
91 |  |  |  | Checking that the labels for “Mobile number” and “Password” clearly indicate what information the user should enter | Should be indicate | Found as per expectation |  |  |  | Passed
92 |  |  |  | Checking Autofill option | User should be filled input field using Autofill option | Found as per expectation |  |  |  | Passed
93 |  |  |  | Checking that all elements of the login page are accessible to users | Should be accessible | Found as per expectation |  |  |  | Passed
94 |  |  |  | Checking that error messages are helpful and guide the user on how to correct mistakes | Should be helpful | Found as per expectation |  |  |  | Passed
95 |  |  |  | Checking that “Sign with Google” and “Sign with Facebook” options work seamlessly and reduce the time to log in | Should be taken small amount of time to login | Found as per expectation |  |  |  | Passed
96 |  |  |  | Checking that users find the “Forget password” process easily not complicated | Should be find it and process it easily | Found as per expectation |  |  |  | Passed
97 |  |  |  | Checking that new users find the “New customer? Register here” link easily and understand that it’s for new account creation | Should be find easily | Found as per expectation |  |  |  | Passed
98 |  |  |  | Verifying Users can log in quickly without any delays or issues. | Should be login without any dealys | Found as per expectation |  |  |  | Passed
99 |  |  |  | Checking that Users can easily find and navigate to the login page from the homepage. | Should be findout easily | Found as per expectation |  |  |  | Passed
100 |  | Default characteristics |  | Verifying that To save login details for future sessions | Should be save for future use | Found as per expectation |  |  |  | Passed
101 |  |  |  | Checking that for quick access using social media credentials | Should be quick access | Found as per expectation |  |  |  | Passed
102 |  |  |  | Checking that login button exact in the same place as per requirement | Should be same place | Found as per expectation |  |  |  | Passed
103 | [9 empty] | Not Executed
Improvement Scopes
'Remember Me' checkbox should be presented for user
The email option should be available for registration.
Place 'Forgot your password' link below Password field

## Bug Report
Bug Reporting
# SL 01
Issue: proper instruction for inavild or blank phone number in alert message.
Reproducing Steps:
1. Goto the URL https://www.pickaboo.com/register/ 2. Click on Login button at the right corner then goto register/ 3. Inputting firstname and lastname with numbers 4. Click Contniue button without input any number
Env: Production
Module: Register
Severity: P1
https://www.loom.com/share/79f2bc79a3674d789b4feb868687aede?sid=0d336079-e395-4f61-9f0b-ae10cb052eb4
Responsible QA: Suvojit Das

## Test Summary Report
Test Case Report
Project Name | BD Shop
Module Name | Sign Up and Sign In | [5 empty] | Total No. | Status |  | Result :
Test Case Version | [6 empty] | 83 | PASS
Written By | Tamanna Zubairi Sana | [5 empty] | 19 | FAIL
Executed By | Tamanna Zubairi Sana | [5 empty] | 1 | Not Executed |  | New Features | Testing Scope | Testing Environment : | Google Chrome Browser
Reviewed By | Ehsanul Alam Sabbir | [5 empty] | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 83 | 19 | 1 | 0 | 103
Grand Total | 83 | 19 | 1 | 0 | 103
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.
GENERAL INFORMATION
Test Stage: |  | Unit Performance |  | Functionality Regression |  | Integration Acceptance |  | System Plot |  | Interface
Specify the testing stage for this test case.
Test Date: |  | mm/dd/yy |  |  |  | System Date,If applicable: |  |  | mm/dd/yy
Tester: |  | Specify the name(s) of who is testing this case scenario. |  |  |  | Test Case Number: |  |  | Specify a unique test number assigned to the test case.
Test Case Description: |  | Provide a brief description of what functionality the case will test.
Result: |  | Pass |  | Fail |  | Incident Number, If applicable: |  |  | Specify the unique identifier assigned to the incident.
INTRODUCTION
Requirement(s) to be tested: |  | Identify the requirements to be tested and include the requirement number and description from the Requirements Traceability Matrix.
Roles and Responsibilites : |  | Describe each project team member and stakeholder involved in the test, and identify their associated responsibility for ensuring the test is executed appropriately.
Set up Procedures: |  | Describe the sequence of actions necessary to prepare for execution of the test.
Stop Procedures: |  | Describe the sequence of actions necessary to terminate the test.
ENVIRONMENTAL NEEDS
Hardware: |  | Identify the qualities and configurations of the hardware required to execute the test case.
Software: |  | Identify system and application software required to execute the test case. Specify any software that the test case will interact with.
Procedural Requirments: |  | Describe any constraints on the test procedures necessary to execute the test case.
TEST
Test Items and Features: |  | Identify and describe the items and features that will be exercised by the test case. Group the test cases into logically related scenarios that test related items and features. For each item or feature, a reference to its associated requirement source should be included.
Input Specifications: |  | Define each input required to execute the test case, and reference any required relationships between inputs.
Procedural Steps: |  | Describe the sequences of actions necessary to prepare and execute the test case. Provide detailed test procedures for each test case; explain precisely how each test case will be executed.
Expected Results of Case: |  | Describe the outcome anticipated from the test case. Specify the criteria to be used to determine whether the item has passed or failed.
ACTUAL RESULTS
Output Specifications: |  | Define all of the outputs and features required of the test case and provide expected values. While executing the test, record and describe the visually observable outputs as they occur. Produce tangible evidence of the output such as a screen print. At the conclusion, describe the actual outcome. Indicate whether the test passed or failed, and identify any discrepancies between the expected results and the actual results.
Test Case Report
GENERAL INFORMATION
Test Stage: | Functionality
Test date: | 2023-09-09 | System Date, if applicable: | N/A
Tester: | Imran Hasan | Test Case Number: | # SL 11
Test Case Description: | User should not register to the system without entering password.
Results: | Fail | Incident Number, if applicable | N/A
INTRODUCTION
Requirement(s) to be tested: | User should enter valid password including at least one uppercase one numeric and minimum length should be eight.
Rules and Responsibilities: | N/A
Set Up Procedures: | 1. Ensure that your device has Internet access 2. Open Google Chrome
Stop Procedures: | 1. Screenshot of that error. 2. Record test result.
ENVIRONMENTAL NEEDS
Hardware: | N/A
Software: | Google Chrome
Procedural Requirements: | N/A
TEST
Test Items and Features: | Password field for user registrations. Requirements source not applicable.
Input Specification: | 1. Email: imranhasan@gmail.com 2. Valid Captcha
Procedural Steps: | 1. Go to the url: https://fatcoupon.com/ 2. Clicked on Sign In Button 3. Clicked on Sign Up button 4. Enter Valid mail and Captcha 5. Keep Password Feild blank 6. Clicked on Sign Up button
Expected Result of the Case: | User should not registered without Entering valid password.
ACTUAL RESULTS
Output Specification: | 1. User can registered without password 2. User can registered with invalid password.

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (103/103)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (1/103)*100 = 0.97
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (83/103)*100 = 80.58
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (19/103)*100 = 18.44
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/100)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A